## Product Delivery, Scope
[19 empty] | Backlog item | Size (scope unit)
Scope (unit: estimated weeks, points, etc.) | 2012-12-01 | 2012-12-15 | 2013-01-01 | 2013-01-14 | 2013-02-01 | 2013-02-14 | 2013-03-01 | 2013-03-15 | 2013-04-01 | 2013-04-15 | 2013-05-01 | 2013-05-15 | 2013-06-01 | 2013-06-15 | 2013-07-01 | 2013-07-17 | 2013-08-02 | 2013-08-16 | Portfolio Snapshot | 7
just for reference scope | 1 | 1 | 3 | 5 | 8 | 13 | 22 | 31 | 41 | 52 | 63 | 74 | 85 | 96 | 105 |  |  |  | Watch List | 5
Historical Scope | 1 | 1 | 3 | 5 | 8 | 13 | 22 | 31 | 45 | 60 | 75 | 90 | 105 | 120 | 129 | 129 | 129 | 129 | Holdings | 4
Current Planned Scope | 1 | 1 | 3 | 5 | 8 | 13 | 22 | 31 | 35 | 45 | 60 | 72 | 84 | 96 | 108 | 120 | 129 | 129 | Quotes | 11
Actual Complete Scope | 1 | 1 | 2 | 5 | 7 | 11 | 15 | 19 | 29 | 40 | 53 | 60 | 74 | 88 | 102 | 113 | 125 | 129 | Markets & News | 6
[19 empty] | Sign In/Out | 6
Dev Effort (unit: pairs, devs, etc.) | [18 empty] | Trxn History | 7
Available Trust | 50% | 50% | 50% | 40% | 16.67% | 28.12% | 48.75% | 31.5% | 43.33% | 18.75% | 62.5% | 68.75% | 68.75% | 68.75% | 68.75% | 68.75% | 68.75% | 68.75% | Equity Trading | 18
Planned Available Dev Effort | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | Option Order | 12
Actual Available Dev Effort | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | Charts | 6
Planned Effective Effort (Utilization) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | FX Order | 5
Effective Effort | 0.5 | 0.5 | 0.5 | 0.4 | 0.5 | 1.125 | 1.95 | 1.575 | 2.6 | 1.125 | 3.75 | 4.125 | 4.125 | 4.125 | 4.125 | 4.125 | 4.125 | 4.125 | App Store/ Pre Login | 3
[19 empty] | Mutual Funds Order | 8
Project Events (time cost in percent) | [18 empty] | Alerts | 6
DRS reviews | 10% | 10% | 10% | 20% | 15% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Feedback | 3
Level 2 estimates | 10% | 10% | 10% | 0% | 20% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Reg loss/external factors | 10% | 10% | 10% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15%
Communications offshore | 10% | 10% | 10% | 15% | 0% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
team Kiev visit/ramp up | 10% | 10% | 10% | 10% | 30% | 20% | 10% | 10% | 10% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cost (in $ or h)
Planned Cost (Forecast) | 60000 | 120000 | 190000 | 260000 | 330000 | 400000 | 470000 | 540000 | 610000 | 680000 | 750000 | 820000 | 890000 | 960000 | 1030000 | 1100000 | 1170000 | 1240000
Actual Cost | 50000 | 115000 | 187000 | 257000 | 329000 | 350000 | 370000 | 450000 | 500000 | 630000 | 721000 | 785000 | 960000 | 1015000 | 1080000 | 1145000 | 1210000 | 1300000
Overtime | 10% | 5% | 5% | 10% | 5% | 7% | 10% | 10% | 10% | 10% | 10% | 20% | 20% | 7% | 5% | 0% | 0% | 10%
Scope Index | 1 | 1 | 0.66667 | 1 | 0.875 | 0.84615 | 0.68182 | 0.6129 | 0.82857 | 0.88889 | 0.88333 | 0.83333 | 0.88095 | 0.91667 | 0.94444 | 0.94167 | 0.96899 | 1
Relative Cost Index | 0.83333 | 0.95833 | 1.4763 | 0.98846 | 1.1394 | 1.0341 | 1.1546 | 1.3596 | 0.98926 | 1.0423 | 1.0883 | 1.1488 | 1.2244 | 1.1534 | 1.1102 | 1.1054 | 1.0673 | 1.0484
Overtime index | 0.1 | 0.05 | 0.05 | 0.1 | 0.05 | 0.07 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.07 | 0.05 | 0 | 0 | 0.1
Note on A15: Dimitre Dimitrov: Moved the end date for delivery from Jul 1 to Aug 2
Note on F16: Dimitre Dimitrov: Demoed and accepted
Note on I16: Dimitre Dimitrov: Demoed and accepted
Note on J16: Dimitre Dimitrov: Demoed and accepted
Note on M16: Dimitre Dimitrov: Demoed and accepted
Note on P16: Dimitre Dimitrov: Demoed and accepted
Note on A19: Dimitre Dimitrov: % Productive Effort… this is the percent of the effort that actually goes towards product development. In this case this is meant to represent only programming and testing… but requirements gathering can be included too… especially if it was part of the original estimations and is being tracked in story points like all other work.
Note on A28: Dimitre Dimitrov: This can factor in all type of things like "demotivation", "not ideal organization", "not ideal requirements", etc… Anything that makes the team not perform at their potential maximum. These factors can be split into their own rows if more fidelity is needed.
Note on A35: Dimitre Dimitrov: If most team memebers need to put about an hour a day overtime this translates to about 15%.
Color Legend:
Demoed and Accepted - these are numbers that are plugged in based on demoed or accepted deliverables
Planned or Baselined - these are initial numbers that reflect the understanding at some point of time
Interpolated or Guessed - these are numbers that are approximated/fabricated with some degree of correctness
Calculated - these are numbers derived by calculations based on other numbers
Numbers Explanations
Scope - this is what is estimated, planned and delivered. The unit may be anything but needs to be consistent.
Dev Effort - this is the effort that is planned to be expanded, or that is actually being expanded.
Project events - these are significant events that change the available effort towards development. If adding more events make sure they are factored in for the calculations by including them in the formula range.
Scope Chart Explanations
Axis:
- left vertical axis shows scope in the unit of estimation (triplet weeks in the example case above)
- right vertical axis shows the percent of effort that goes towards the product (this is percent of the planned utilization... for example if planned utilization was 50% then an actual available effort of 50% will translate in 100% "Available Trust")
Lines:
- Thick lines show the state at any moment
- Thin lines are for reference and can be used to infer some tendencies and expectations.
Performance Indexes Chart Explanations
This chart shows how much "value" is produced compared to planed. And how much it cost to produce this value compared to the planned cost.
The planned cost and actual cost are plotted against the secondary axis.
It also depicts the hidden cost of overtime which is shown as accumulative to draw attention on the fact that it does not only reflect a momentary state.
Backlog Item table
This is for reference only, but is needed to figure out what is the "Actual Complete" based on what backlog items have been delivered or to approximate based on the known progress.
The goal of this document is to have all the planned scope visible and then to plot the actual scope against it for the purpose of eye-balling the progress and making long term projections.
Its goal is not to be a detailed and complete tracking of minute details around the project deliverables.
The nature of extrapolating, forecasting and the original estimations themselves is such that accuracy is questionably important. Please do not waste time to enter "correct" numbers, and instead enter numbers that are as close to real as you have available at the time.